# Proforma Term Sheet

THIS TERM SHEET FOR ENERGY STORAGE SERVICES AGREEMENT (“**Term Sheet**”) is entered into as of [\_\_\_\_\_], 2020 (the “**Effective Date**”), between Central Coast Community Energy, CleanPowerSF, Marin Clean Energy, Peninsula Clean Energy, Redwood Coast Energy Authority, San Jose Clean Energy, Silicon Valley Clean Energy and Sonoma Clean Power, (collectively, the “**Joint CCAs**”) and [*Respondent*] (“**Respondent**”). This Term Sheet includes the key commercial terms and conditions to be included in a proposed energy storage service agreement (“**ESSA**”) to be negotiated between the Joint CCAs (“**Buyer**”) and [*e.g., Project Company LLC*] (“**Seller**”) (the “**Proposed Transaction**”). As used herein, Buyer and Seller are each a “**Party**” and collectively the “**Parties**.” Notwithstanding anything herein to the contrary, that until a definitive agreement is approved by Buyer’s Joint Procurement Authority and signed and delivered by each Buyer and Seller, no Party shall have any legal obligations, expressed or implied, or arising in any other manner under this Term Sheet to continue negotiations or enter into the Proposed Transaction or the ESSA.

1. **ESSA Terms and Conditions**.

|  |  |
| --- | --- |
| **Storage Product:** | **Option 1:** RA Product – includes Resource Adequacy Benefits only. “**Resource Adequacy Benefits**” means the rights and privileges attached to the Storage Facility that satisfy any entity’s resource adequacy obligations, and includes any local, zonal or otherwise locational attributes associated with the Storage Facility, in addition to flex attributes. [***Please note that, subject to the agreement of Buyer and Seller, the ESSA for an RA Only product may take the form of an EEI confirmation between Buyer and Seller.*]** **Option 2:** Storage Product – includes all energy, capacity, Resource Adequacy Benefits, and ancillary services produced by or associated with the Storage Facility.Buyer receives full dispatchable rights and energy revenues earned.**Option 3:** RA Product with Revenue Sharing – includes Resource Adequacy Benefits, and percent sharing of benefits (TBD) of revenues from energy and ancillary services produced by or associated with the Storage Facility.Seller will schedule and dispatch the energy. **Option 4:** RA Product + Energy Discharge – includes Resource Adequacy Benefits and blocks of 8 hours of discharge at the hours of Buyer’s choosing.**Option 5:** Unique Offer [*Include detail.*] |
| **Storage Facility:** | “**Storage Facility**” or “**Project**” means the [\_\_\_] project, located in [County], in the State of [California].  |
| **Storage Capacity:** | [XX] MWAC |
| **RA Capacity:** | [XX] MW [NQC] |
| **Contract Price:** | RA Product: $[XX]/kW-month of delivered RA Capacity.Storage Product: $[XX]/kW-month of Storage Capacity, as adjusted for the Storage Capacity Test (as set forth in the ESSA), multiplied by the actual round-trip efficiency, and subject to the Availability Adjustment. RA Product with Revenue Sharing: [TBD]RA Product + Energy Discharge: [TBD]Unique Offer: [TBD] |
| **Delivery Term:** | [\_\_\_] Contract Years from the Commercial Operation Date, with each 12-month period following the Commercial Operation Date considered a “**Contract Year**.” |
| **Commercial Operation Date:** | The “**Commercial Operation Date**” or “**COD**” shall be the later of (a) the Expected Commercial Operation Date or (b) the date on which Commercial Operation is achieved. “**Commercial Operation**” means the condition existing when Seller has fulfilled the following conditions precedent in the ESSA and provided notice of same to Buyer, including providing a certificate from an independent engineer to Buyer with respect to subparts (i), (iii), (iv) and (v): 1. Storage Facility has met all Interconnection Agreement requirements or Agreements required to set Dynamic Transfer and is capable of receiving charging energy from, and delivering discharging energy to, the CAISO Balancing Authority;
2. Seller has provided Buyer with a copy of written notice from the CAISO that the Storage Facility has achieved Full Capacity Deliverability Status (as defined in the CAISO tariff), if applicable;
3. Seller has provided Buyer Maximum Import Capability (MIC) rights for full RA Product, if applicable;
4. Commissioning of equipment has been completed in accordance with the manufacturer’s specifications;
5. 95% of Storage Capacity has been installed and commissioned;
6. Storage Facility has successfully completed all testing required by prudent utility practices or any requirement of law to operate the Storage Facility;
7. All applicable permits and government approvals required for the operation of the Storage Facility have been obtained;
8. Seller has obtained all real property rights;
9. Security requirements for the Delivery Term have been met; and
10. Insurance requirements for the Storage Facility have been met, with evidence provided in writing to Buyer.

Seller shall provide notice of expected COD to Buyer in writing no less than sixty (60) days in advance of such date. Seller shall notify Buyer in writing when Seller believes that it has provided the required documentation to Buyer and met the conditions for achieving COD. Buyer shall have five (5) Business Days to approve or reject Seller’s request for COD. Upon Buyer’s approval of Seller’s achievement of COD, Buyer shall provide Seller with written acknowledgement of the COD. |
| **Guaranteed Construction Start Date:** | The “**Guaranteed Construction Start Date**” means the following date [\_\_\_\_\_\_\_], subject to extensions on a day-for-day basis due to Force Majeure or delays caused by transmission provider (e.g., the CAISO) or transmission owner (e.g., PG&E) that are outside of the reasonable control of Seller. Such day-for-day extensions, including for Force Majeure, shall be no longer than one-hundred twenty (120) days on a cumulative basis. For clarity, these permitted extensions extend both the Guaranteed Construction Start Date and the Guaranteed COD simultaneously.In the event that Seller fails to achieve the Guaranteed Construction Start Date, Seller shall pay delay damages to Buyer, (the “**Daily Delay Damages**”) for each day of delay, in the amount of the Development Security divided by 120. The Daily Delay Damages shall be refundable to Seller if, and only if, Seller achieves COD on or before the Guaranteed COD.Failure to achieve Guaranteed Construction Start within 180 days of the Guaranteed Construction Start Date shall constitute an Event of Default, and Buyer shall have the right, in its sole discretion, to terminate the ESSA and retain the Development Security. |
| **Guaranteed Commercial Operation Date:** | The “**Guaranteed Commercial Operation Date**” or “**Guaranteed COD**” means the following date [\_\_\_\_\_\_\_], subject to extensions on a day-for-day basis due to Force Majeure or delays caused by transmission provider (e.g., the CAISO) or transmission owner (e.g., PG&E) that are outside of the reasonable control of Seller. Such day-for-day extensions, including for Force Majeure, shall be no longer than one-hundred twenty (120) days on a cumulative basis. For clarity, these permitted extensions extend both the Guaranteed Construction Start Date and the Guaranteed COD simultaneously.If the Seller does not achieve COD of the Facility by the Guaranteed COD, Seller shall pay Delay Damages to the Buyer for each day of delay until Seller achieves COD.“**Delay Damages**” are equal to the Development Security divided by 60. Delay Damages shall be paid for each day of delay and shall be paid to Buyer in advance monthly. A prorated amount will be returned to Seller if COD is achieved during the month for which Delay Damages were paid in advance.Failure to achieve COD within 60 days of the Guaranteed COD shall constitute an Event of Default, and Buyer shall have the right, in its sole discretion, to terminate the ESSA and retain the Development Security. |
| **Project Interconnection Point:** | The Project shall interconnect to [*e.g., XX substation*] (the “**Interconnection Point**”). Seller shall be responsible for all costs of interconnecting the Project to the Interconnection Point. |
| **Delivery Point:** | “**Delivery Point** means [the Storage Facility Pnode] on the CAISO grid. |
| **Deliverability:** | The Facility will have Full Capacity Deliverability Status by the Commercial Operation Date. |
| **Site Control:** | Seller shall maintain site control throughout the Delivery Term. |
| **Permits and Approvals:** | Seller shall obtain any and all permits and approvals, including without limitation, environmental clearance under the California Environmental Quality Act (“**CEQA**”) or other environmental law, from the local jurisdiction where the Project is or will be constructed. Buyer is simply purchasing power and does not intend to be the lead agency for the Project. |
| **Project Development Milestones:** | * [date] – receipt of CEC pre-certification
* [date] – execution of Interconnection Agreement
* [date] – procurement of major equipment
* [date] – obtain federal and state discretionary permits
* [date] – Guaranteed Construction Start Date
* [date] – obtain Full Capacity Deliverability Status, if applicable
* [date] – Guaranteed Commercial Operation Date
 |
| **Maximum Storage Level:** | [XX] MWh [number in MWh representing maximum amount of energy that may be discharged from the Storage Facility] |
| **Minimum Storage Level:** | [XX] MWh [number in MWh representing the lowest level to which the Storage Facility may be discharged] |
| **Maximum Charging Capacity:** | [XX] MW [highest level at which Storage Facility may be charged]  |
| **Maximum Discharging Capacity:** | [XX] MW [number in MW representing the highest level at which the Storage Facility may be discharged] |
| **Maximum State of Charge (SOC) during Charging:** | 100%  |
| **Minimum State of Charge (SOC) during Discharging:** | 0% |
| **Maximum Round-Trip Efficiency:** | [XX]% [peak efficiency of conversion between charging energy and discharging energy (i.e. ratio of maximum charging energy to maximum discharging energy)]If actual round-trip efficiency is greater than or equal to Maximum Round-Trip Efficiency, then for purposes of calculating the monthly payment amount, the actual round-trip efficiency will be deemed to be 100%. |
| **Minimum Round-Trip Efficiency:** | [XX]% [minimum guaranteed efficiency of conversion between charging energy and discharging energy (i.e. ratio of minimum charging energy to minimum discharging energy)] measured at the point of interconnection.If actual round-trip efficiency is less than Minimum Round-Trip Efficiency, then for purposes of calculating the monthly payment amount, the actual round-trip efficiency will be deemed to be 0%. |
| **Ramp Rate Range:** | [XX] MW/minute to [XX] MW/minute |
| **Monthly/Annual Cycles:** | [Number of times per contract term Buyer may fully charge and discharge the Storage Facility. A full charge will be deemed to have occurred when the cumulative amount of energy added to the Storage Facility over the course of a calendar month equals the Maximum Storage Level. This could occur in one continuous charge or over multiple charges, even if some energy is discharged in between. The inverse is true for a full discharge.] |
| **Additional Energy Storage Products:** | All ancillary services and environmental attributes produced by the Storage Facility. |
| **Ancillary Services Capability:** | [List frequency regulation, spin, regulation up, regulation down, etc., and specify relevant operating parameters for each.] |
| **Scheduling Coordinator:** | [Seller/Buyer]For RA Product: Seller or Seller’s agent shall act as Scheduling Coordinator (as defined by the CAISO) for the Storage Facility. Seller shall be financially responsible for such services and shall pay for all CAISO charges and retain all CAISO payments.For Storage Product: Buyer or Buyer’s agent shall act as Scheduling Coordinator (as defined by the CAISO) for the Storage Facility. Buyer shall be financially responsible for such services and shall pay for all CAISO charges (including for charging energy) and retain all CAISO payments (including for discharging energy); provided however, that notwithstanding the foregoing, Seller shall assume all liability and reimburse Buyer for any and all costs or charges (i) incurred by Buyer because of Seller’s failure to perform, (ii) incurred by Buyer because of any outages for which notice has not been provided as required, (iii) associated with Resource Adequacy Capacity (as defined by the CAISO) from the Storage Facility (including Non-Availability Charges (as defined by the CAISO)), if applicable or (iv) to the extent arising as a result of Seller’s failure to comply with a timely Buyer Curtailment Order if such failure results in incremental costs to Buyer. Outage and curtailment notifications will be required by Buyer as well as access to Storage Facility charging and discharging data.  |
| **Station Use:** | Buyer will not be responsible for Station Use and Station Use will not be provided by the Storage Facility. Expected Station Use: [XX] MWh per year. |
| **Guaranteed Storage Availability:** | [98%] [percentage of hours each month that Seller agrees the Storage Facility will be available]  |
| **Availability Adjustment:** | The Availability Adjustment (“**AA**”), which is calculated as follows:1. If the monthly storage availability is greater than or equal to the Guaranteed Storage Availability, then:

AA = 100%1. If the monthly storage availability is less than the Guaranteed Storage Availability, but greater than or equal to 70%, then:

AA = 100% - [(98% - monthly storage availability) × 2]1. If the monthly storage availability is less than 70%, then:

AA = 0 |
| **Local Workforce:** | [include % of workforce from Buyer’s service territory Seller will utilize] |
| **Monthly Settlement and Invoice:** | Within ten (10) days after the end of each month of the Delivery Term, Seller shall send a detailed invoice to Buyer for the amount due for Product delivered during such month. The invoice shall include all information necessary to confirm the amount due.Payment for undisputed amounts shall be due to the applicable party thirty (30) days from the invoice date, with disputed payments subject to Buyer’s billing dispute process. |
| **Operations and Maintenance:** | During the months of June through September Seller shall not schedule any non-emergency maintenance that reduces the energy storage capability of the Storage Facility by more than ten percent (10%), unless (i) such outage is required to avoid damage to the Storage Facility, (ii) such maintenance is necessary to maintain equipment warranties and cannot be scheduled outside the months of June through September, (iii) such outage is required in accordance with prudent electrical practices, or (iv) the Parties agree otherwise in writing. |
| **Progress Reporting:** | After execution of the ESSA, Seller shall provide a quarterly report until the COD followed by a monthly report to Buyer that (a) describes the progress towards meeting the Storage Facility Development Milestones; (b) identifies any missed Storage Facility Development Milestones, including the cause of the delay; and (c) provides a detailed description of Seller’s corrective actions to achieve the missed Storage Facility Development Milestones and all subsequent Storage Facility Development Milestones by the Guaranteed Commercial Operation Date. If applicable, progress reporting shall also include reporting on small business activities. In the event Seller misses any Project Development Milestones and cannot reasonably demonstrate a plan for completing the Facility by the Guaranteed COD, Buyer shall have the right to terminate the ESSA and retain the Development Security as damages, in addition to any other remedies it may have at law or equity. |
| **Credit Requirements:** | The Seller shall post security as follows:Development Security – $90/kW of Guaranteed CapacityPerformance Security – $105/kW of Guaranteed CapacityTo secure its obligations under the ESSA, Seller shall deliver the Development Security to Buyer within thirty (30) days of the Effective Date. Development Security shall be in the form of cash or a Letter of Credit. Within five (5) Business Days following any draw by Buyer on the Development Security or the Performance Security, Seller shall replenish the amount drawn such that the security is restored to the applicable amount.To secure its obligations under the ESSA, Seller shall deliver Performance Security to Buyer on or before the Commercial Operation Date. |
| **Compliance with Laws:**  | Seller shall comply with all federal, state and local laws, statutes, ordinances, rules and regulations, and the orders and decrees of any courts or administrative bodies or tribunals, including, without limitation those related to employment discrimination and prevailing wage, non-discrimination and non-preference; conflict of interest; environmentally preferable procurement; single serving bottled water; gifts; and disqualification of former employees. |
| **Business Tax: [[1]](#footnote-1)**  | The Seller shall obtain a City business tax certificate or exemption, if qualified, and will maintain such certificate or exemption for the Proposed Transaction term.  |
| **Assignment:** | Neither Party may assign the ESSA without prior written consent of the other party, which will not be unreasonably withheld; provided, that Seller has the right to assign the ESSA as collateral for any financing or refinancing of the Facility without the consent of Buyer. Any direct or indirect change of control of Seller (whether voluntary or by operation of law) will be deemed an assignment and will require the prior written consent of Buyer, which will not be unreasonably withheld. Seller shall pay Buyer’s reasonable expenses, including attorneys’ fees, incurred to provide consents, estoppels, or other required documentation in connection with Seller’s financing for the Facility. Buyer will have no obligation to provide any consent, or enter into any agreement, that materially and adversely affects any of Buyer’s rights, benefits, risks or obligations under the ESSA, or to modify such ESSA. |
| **No Recourse to Members of Buyer[[2]](#footnote-2)** | Buyer is organized as a Joint Powers Authority in accordance with the Joint Exercise of Powers Act of the State of California (Government Code Section 6500, et seq.) and is a public entity separate from its constituent members. Buyer will solely be responsible for all debts, obligations and liabilities accruing and arising out of this Confirmation. Seller will have no rights and will not make any claims, take any actions or assert any remedies against any of Buyer’s constituent members, or the officers, directors, advisors, contractors, consultants or employees of Buyer or Buyer’s constituent members, in connection with this Confirmation. |
| **Appropriation of Funds:[[3]](#footnote-3)** | [Buyer is a municipal corporation and is precluded under the California State Constitution and applicable law from entering into obligations that financially bind future governing bodies, and, therefore, nothing in the ESSA shall constitute an obligation of future legislative bodies of the City to appropriate funds for purposes of the ESSA; provided, however, that (a) Buyer has created and set aside the Designated Fund for payment of its obligations under the ESSA and (b) subject to the requirements and limitations of applicable law and taking into account other available money specifically authorized by the San José City Council and allocated and appropriated to the San José Clean Energy’s obligations, Buyer agrees to establish San José Clean Energy rates and charges that are sufficient to maintain revenues in the Special Fund necessary to pay its obligations under the ESSA and all of Buyer’s payment obligations under its other contracts for the purchase of energy for San José Clean Energy. Buyer’s payment obligations under the ESSA are special limited obligations of Buyer payable solely from the Special Fund and are not a charge upon the revenues or general fund of the City of San José or upon any non- San José Clean Energy moneys or other property of the Community Energy Department or the City of San José. Buyer shall provide Seller with reasonable access to account balance information with respect to the San José Clean Energy Designated Fund during the term of the ESSA. |
| **Designated Fund and Limited Obligation:** | **Designated Fund**. Buyer’s payment obligations under this Agreement shall be paid from a Department of Community Energy designated fund (“Designated Fund”) that shall be used solely for San José Clean Energy costs and expenses, including the obligations under this Agreement. Subject to the requirements and limitations of Applicable Law and taking into account other available money specifically authorized by the San José City Council and allocated and appropriated to the San José Clean Energy’s obligations, the Buyer agrees to establish San José Clean Energy rates and charges that are sufficient to maintain revenues in the Designated Fund necessary to pay its obligations under this Agreement and all of Buyer’s payment obligations under its other contracts for the purchase of energy for San José Clean Energy. Buyer shall provide Seller with reasonable access to account balance information with respect to the San José Clean Energy Designated Fund during the Term. **Limited Obligations**. Buyer’s payment obligations are special limited obligations of the Buyer payable solely from the Designated Fund. Buyer’s payment obligations under this Agreement are not a charge upon the revenues or general fund of the City of San José or upon any non- San José Clean Energy moneys or other property of the Community Energy Department or the City of San José.] |
| **Force Majeure:** | “Force Majeure Event” means any act or event that delays or prevents a Party from timely performing all or a portion of its obligations under this Agreement or from complying with all or a portion of the conditions under this Agreement if such act or event, despite the exercise of reasonable efforts, cannot be avoided by and is beyond the reasonable control (whether direct or indirect) of and without the fault or negligence of the Party relying thereon as justification for such delay, nonperformance, or noncompliance.Without limiting the generality of the foregoing, so long as the following events, despite the exercise of reasonable efforts, cannot be avoided by, and are beyond the reasonable control (whether direct or indirect) of and without the fault or negligence of the Party relying thereon as justification for such delay, nonperformance or noncompliance, a Force Majeure Event may include an act of God or the elements, such as flooding, lightning, hurricanes, tornadoes, or ice storms; explosion; fire; volcanic eruption; flood; epidemic; landslide; mudslide; sabotage; terrorism; earthquake; or other cataclysmic events; an act of public enemy; war; blockade; civil insurrection; riot; civil disturbance; or strikes or other labor difficulties caused or suffered by a Party or any third party except as set forth below. Notwithstanding the foregoing, the term “Force Majeure Event” does not include (i) economic conditions that render a Party’s performance of this Agreement at the Contract Price unprofitable or otherwise uneconomic (including Buyer’s ability to buy Energy at a lower price, or Seller’s ability to sell Energy at a higher price, than the Contract Price); (ii) Seller’s inability to obtain permits or approvals of any type for the construction, operation, or maintenance of the Facility; (iii) the inability of a Party to make payments when due under this Agreement, unless the cause of such inability is an event that would otherwise constitute a Force Majeure Event as described above that disables physical or electronic facilities necessary to transfer funds to the payee Party; (iv) a Curtailment Period, except to the extent such Curtailment Period is caused by a Force Majeure Event; (v) Seller’s inability to obtain sufficient labor, equipment, materials, or other resources to build or operate the Facility except to the extent such inability is caused by a Force Majeure Event; (vi) a strike, work stoppage or labor dispute limited only to any one or more of Seller, Seller’s Affiliates, Seller’s contractors, their subcontractors thereof or any other third party employed by Seller to work on the Facility; (vii) any equipment failure except if such equipment failure is caused by a Force Majeure Event; or (viii) events otherwise constituting a Force Majeure Event that prevent Seller from achieving Construction Start or Commercial Operation of the Storage Facility, except to the extent expressly permitted as an extension under the ESSA. |
| **Other Standard Contract Terms to be included in the ESSA:** | **Event of Default**: Events of Default shall include, but not be limited to, failure to pay any amounts when due, breach of representations and warranties, failure to perform covenants and material obligations in the ESSA, bankruptcy, assignment not permitted by the ESSA, Seller failure to achieve Construction Start within one hundred eighty (180) days of Guaranteed Construction Start Date, and Seller failure to achieve Commercial Operation within sixty (60) days after the Guaranteed Commercial Operation Date. **Indemnification**: Seller to indemnify Buyer for third party claims arising from Seller’s negligence, willful misconduct, or breach of the ESSA.**Governing Law**: State of California**Venue**: Santa Clara County |
| **Definitions:** | The following terms, when used herein with initial capitalization, shall have the meanings set forth below:“**CAISO**” means the California Independent System Operator.“**CAISO Tariff**” means the California Independent System Operator Corporation Agreement and Tariff, Business Practice Manuals (BPMs), and Operating Procedures, including the rules, protocols, procedures and standards attached thereto, as the same may be amended or modified from time-to-time and approved by FERC.“**CEC**” means the California Energy Commission, or any successor agency performing similar statutory functions.“**CEQA**” means the California Environmental Quality Act.“**Delivery Term**” shall mean the period of Contract Years beginning on the Commercial Operation Date.“**Full Capacity Deliverability Status**” has the meaning set forth in the CAISO Tariff.“**Letter(s) of Credit**” means one or more irrevocable, standby letters of credit issued by a U.S. commercial bank or a foreign bank with a U.S. branch with such bank (a) having a credit rating of at least A- with an outlook designation of “stable” from S&P or A3 with an outlook designation of “stable” from Moody’s or (b) being reasonably acceptable to Buyer.“**MW**” means megawatts in alternating current, unless expressly stated in terms of direct current.“**MWh**” means megawatt-hour measured in alternating current, unless expressly stated in terms of direct current. |
|  |  |

1. **Neither Party Obligated to Enter Into Proposed Transaction**. This Term Sheet is intended to provide an overview of the Proposed Transaction and is not intended to constitute a binding contract or an offer to enter into a ESSA with respect to the Proposed Transaction and does not obligate either Party to enter into the Proposed Transaction or execute any agreement, including the ESSA, in connection with the Proposed Transaction. Neither Party will be deemed to have agreed to the ESSA and will not be bound by any term thereof, unless and until authorized representatives of both Parties execute final definitive documents, enforceable in accordance with their terms.
2. **Other Agreements**. In connection with this Term Sheet, Seller shall execute that certain Exclusivity Agreement (“**Exclusivity Agreement**”) with Buyer and provide a Shortlist Deposit (as defined in such agreement) of $3 per KW to Buyer within three (3) Business Days after execution of the Exclusivity Agreement. The Shortlist Deposit will be returned in accordance with, and subject to, the terms of the Exclusivity Agreement.
3. **Expenses**. Each Party will pay its own costs and expenses (whether internal or out-of-pocket, and whether for legal, financial, technical, or other consultants, or other purposes) in connection with the Term Sheet and any definitive agreements.
4. **Termination**. This Term Sheet will terminate upon the earlier of (a) execution of the ESSA or (b) expiration of the Exclusivity Period (as defined in the Exclusivity Agreement), as such Exclusivity Period may be extended by the Parties in accordance with the Exclusivity Agreement.
5. **Governing Law**. This Term Sheet is governed by, and construed in accordance with, the laws of the State of California.
6. **Counterparts**. This Term Sheet may be executed in counterparts, each of which will be enforceable against the Parties actually executing such counterparts, and all of which together will constitute one instrument. Delivery of an executed signature page of this Term Sheet by email transmission of a PDF image shall be the same as delivery of an original executed signature page.
7. **Prior Agreements**. This Term Sheet supersedes all prior communications and agreements, oral or written, between the Parties regarding the subject matter herein contemplated.
8. **Assignment**. This Term Sheet will be binding upon and inure to the benefit of the Parties and their respective successors and permitted assigns. Neither Party will assign, pledge or otherwise transfer this Term Sheet or any right or obligation under this Term Sheet without first obtaining the other Party’s prior written consent (which consent will not be unreasonably withheld, delayed, or encumbered).
9. **No Consequential Damages**. IN NO EVENT SHALL EITHER PARTY, ITS AFFILIATES AND/OR REPRESENTATIVES BE LIABLE FOR ANY LOST OR PROSPECTIVE PROFITS OR ANY OTHER CONSEQUENTIAL, INCIDENTAL, SPECIAL, PUNITIVE, INDIRECT OR EXEMPLARY DAMAGES UNDER OR IN RESPECT TO THIS TERM SHEET.

IN WITNESS WHEREOF, the Parties have signed this Term Sheet effective as of the Effective Date.

|  |  |
| --- | --- |
| **[*JOINT CCAS/BUYER*]** | **[*RESPONDENT/SELLER***] |
| By: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_Printed Name: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_Title: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ | By: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_Printed Name: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_Title: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |

#

1. This language is applicable if San Jose is the Buyer. [↑](#footnote-ref-1)
2. This language is applicable if the Buyer is either the new JPA or a CCA that is a JPA. [↑](#footnote-ref-2)
3. This language is applicable if San Jose is the Buyer. [↑](#footnote-ref-3)